## Budget Justification
Task ID | Task Description | Resources | [6 empty] | Task Total Cost
|  | Labor |  |  |  |  | Other Cost
|  | Team leads | Team members | Working Hours | Hourly Rate | Estimated cost | Material and Equipment | Miscellaneous
1 | Project Initiation Phase
1.1 | Hold Project Kickoff Meeting
1.1.1 | Define objectives, ultimate goal, and assign leadership roles | 7 |  | 8 | 38 | 2128 |  |  | 2128
2 | Project Planning Phase | [7 empty] | 0
2.1 | Define Requirements | [7 empty] | 0
2.1.1 | Customer Requirements |  |  |  |  | 0 |  | 1000 | 1000
2.1.1.1 | Conduct surveys, analyze service demand, and validate needs | 4 | 3 | 227 | 35 | 55750 |  |  | 55750
2.1.2 | Service Requirements | [7 empty] | 0
2.1.2.1 | Define seasonal maintenance services | 1 |  | 8 | 40 | 320 |  |  | 320
2.1.2.2 | Identify necessary equipment | 4 | 2 | 8 | 35 | 1680 |  |  | 1680
2.1.2.3 | Set safety and quality standards | 6 |  | 8 | 38 | 1824 |  |  | 1824
2.2 | Supply Chain and Equipment Procurement | [5 empty] | 65000 |  | 65000
2.2.1 | Identify vendors | 3 |  | 80 | 38 | 9120 |  |  | 9120
2.2.2 | Select cost-effective suppliers | 2 | 1 | 50 | 35 | 5250 |  |  | 5250
2.2.3 | Plan logistics and delivery schedules | 3 | 2 | 200 | 35 | 35000 |  |  | 35000
2.3 | Risk Management | [6 empty] | 5000 | 5000
2.3.1 | Identify risks | 5 | 1 | 16 | 35 | 3360 |  |  | 3360
2.3.2 | Develop risk management plan | 5 | 1 | 24 | 35 | 5040 |  |  | 5040
2.3.3 | Establish mitigation strategies | 5 | 3 | 40 | 35 | 11200 |  |  | 11200
2.3.4 | Legal | [6 empty] | 10000 | 10000
3 | Project Execution Phase | [7 empty] | 0
3.1 | Develop UniClean Service Platform | [5 empty] | 5000 |  | 5000
3.1.1 | Design and develop a user-friendly web platform | 5 | 2 | 150 | 35 | 36750 |  |  | 36750
3.1.2 | Implement platform features | 3 | 2 | 100 | 35 | 21000 |  |  | 21000
3.1.3 | Test platform for performance and user experience | 2 | 4 | 80 | 35 | 16800 |  |  | 16800
3.2 | Operational Execution | [6 empty] | 24000 | 24000
3.2.1 | Recruit eligible student workers | 5 | 1 | 48 | 35 | 10080 |  |  | 10080
3.2.2 | Conduct training sessions | 3 | 2 | 56 | 35 | 9800 |  |  | 9800
3.2.3 | Assign shifts and scheduling | 4 | 1 | 16 | 36 | 2880 |  |  | 2880
3.2.4 | Establish customer service support | 1 | 2 | 24 | 35 | 2520 |  |  | 2520
3.3 | Test and Pilot Service | [7 empty] | 0
3.3.1 | Launch pilot service | 7 | 8 | 8 | 35 | 4200 |  |  | 4200
3.3.2 | Monitor customer feedback, response time, and cost efficiency | 4 | 2 | 300 | 35 | 63000 |  |  | 63000
3.3.3 | Make adjustments based on pilot test results | 5 | 4 | 56 | 35 | 17640 |  |  | 17640
3.4 | Service Deployment | [7 empty] | 0
3.4.1 | Roll out subscription-based services | 6 | 6 | 51 | 35 | 21423 |  |  | 21423
3.4.2 | Scale operations based on forecasted demand and customer feedback | 4 | 4 | 82.5 | 35 | 23100 |  |  | 23100
4 | Project Closing Phase | [7 empty] | 0
4.1 | Monitoring and Control | [7 empty] | 0
4.1.1 | Track customer satisfaction, retention, and service quality | 1 | 2 | 813 | 29.7 | 24146 |  |  | 24146
4.1.2 | Address operational inefficiencies and improve service offerings | 4 | 2 | [5 empty] | 0
4.1.3 | Conduct weekly review meetings for performance evaluation | 7 | 8 | [5 empty] | 0
4 | Project Closing Phase | [7 empty] | 0
4.12 | Final Review and Closure | [7 empty] | 0
4.2.1 | Document lessons learned, financial analysis, and customer insights | 1 | 2 | 40 | 35 | 4200 |  |  | 4200
4.2.2 | Prepare recommendations for future expansion and service enhancements | 1 | 2 | 56 | 35 | 5880 |  |  | 5880
| Cost |  |  |  |  | 394091 | 70000 | 40000 | 504091
| Contigency@15% | [7 empty] | 75613.65
| Total cost | [7 empty] | 579704.65