## Sheet1
Task ID | Task Description | Project Manager | Finance Manager | Resource Manager | Operations Manager 1 | Operations Manager 2 | Service Platform Manager | Customer Relations Manager
1 | Project Initiation Phase
1.1 | Hold Project Kickoff Meeting
1.1.1 | Define objectives, ultimate goal, and assign leadership roles | A | R | R | R | R | R | R
2 | Project Planning Phase
2.1 | Define Requirements
2.1.1 | Customer Requirements
2.1.1.1 | Conduct surveys, analyze service demand, and validate needs | C | I | C | R | R | C | A
2.1.2 | Service Requirements
2.1.2.1 | Define seasonal maintenance services | A | I | I | R | R | C | I
2.1.2.2 | Identify necessary equipment | C | I | I | I | A,R | C | I
2.1.2.3 | Set safety and quality standards | A | C | C | R | R | R | C
2.2 | Supply Chain and Equipment Procurement
2.2.1 | Identify vendors | I | I | C | C | A | R | I
2.2.2 | Select cost-effective suppliers | C | R | C | I | A | C | C
2.2.3 | Plan logistics and delivery schedules | C | I | C | I | A,R | C | C
2.3 | Risk Management
2.3.1 | Identify risks | A | C | C | R | R | R | I
2.3.2 | Develop risk management plan | A | C | C | R | R | R | I
2.3.3 | Establish mitigation strategies | A | C | C | R | R | R | I
3 | Project Execution Phase
3.1 | Develop UniClean Service Platform
3.1.1 | Design and develop a user-friendly web platform | C | C | I | I | I | A,R | R
3.1.2 | Implement platform features | R | I | I | I | I | A | C
3.1.3 | Test platform for performance and user experience | C | I | I | I | I | A | R
3.2 | Operational Execution
3.2.1 | Recruit eligible student workers | C | I | R | A | C | I | I
3.2.2 | Conduct training sessions | R | I | C | A | C | I | C
3.2.3 | Assign shifts and scheduling | C | I | I | A,R | C | I | C
3.2.4 | Establish customer service support | C | I | C | C | C | R | A
3.3 | Test and Pilot Service
3.3.1 | Launch pilot service | A | C | C | R | R | R | C
3.3.2 | Monitor customer feedback, response time, and cost efficiency | A | R | I | R | R | C | R
3.3.3 | Make adjustments based on pilot test results | A | I | R | R | R | R | C
3.4 | Service Deployment
3.4.1 | Roll out subscription-based services | A | C | I | R | R | R | C
3.4.2 | Scale operations based on forecasted demand and customer feedback | A | I | C | R | R | C | C
3.5 | Monitoring and Control
3.5.1 | Track customer satisfaction, retention, and service quality | C | I | I | R | C | C | A
3.5.2 | Address operational inefficiencies and improve service offerings | C | I | R | R | A,R | R | R
3.5.3 | Conduct weekly review meetings for performance evaluation | A,R | C | R | R | R | R | R
4 | Project Closing Phase
4.1 | Final Review and closure
4.1.1 | Document lessons learned, financial analysis, and customer insights | A,R | R | C | C | C | C | R
4.1.2 | Prepare recommendations for future expansion and service enhancements | A,R | C | C | C | C | C | C