## Sheet1
ID | Task
1 | 1.0 Project Initiation Phase
2 | 1.1 Hold Project Kickoff Meeting
3 | 1.1.1 Define objectives, ultimate goal, and assign leadership roles
4 | 2.0 Project Planning Phase
5 | 2.1 Define Requirements
6 | 2.1.1 Customer Requirements
7 | 2.1.1.1 Conduct surveys, analyze service demand, and validate needs
8 | 2.1.2 Service Requirements
9 | 2.1.2.1 Define seasonal maintenance services (snow removal, leaf cleanup, etc.)
10 | 2.1.2.2 Identify necessary equipment (snowblowers, shovels, leaf blowers, etc.)
11 | 2.1.2.3 Set safety and quality standards for service execution
12 | 2.2 Supply Chain and Equipment Procurement
13 | 2.2.1 Identify vendors for maintenance equipment and materials
14 | 2.2.2 Select cost-effective suppliers and negotiate contracts
15 | 2.2.3 Plan logistics and delivery schedules for procurement
16 | 2.3 Risk Management
17 | 2.3.1 Identify risks (Weather disruptions, equipment failure, labor shortages)
18 | 2.3.2 Develop risk management plans
19 | 2.3.3 Establish mitigation strategies and contingency plans
20 | 3.0 Project Execution Phase
21 | 3.1 Develop UniClean Service Platform
22 | 3.1.1 Design and develop a user-friendly web platform
23 | 3.1.2 Implement features: customer registration, scheduling, notifications, feedback
24 | 3.1.3 Test platform for performance and user experience
25 | 3.2 Operational Execution
26 | 3.2.1 Recruit eligible workforce
27 | 3.2.2 Conduct training sessions on service delivery (SOP) and safety protocols
28 | 3.2.3 Assign shifts, track worker availability, and optimize scheduling
29 | 3.2.4 Establish customer service support for issue resolution
30 | 3.3 Test and Pilot Service
31 | 3.3.1 Launch pilot service
32 | 3.3.2 Monitor customer feedback, response time, and cost efficiency
33 | 3.3.3 Make adjustments based on pilot test results
34 | 3.4 Service Deployment
35 | 3.4.1 Roll out subscription-based services
36 | 3.4.2 Scale operations based on forecasted demand and customer feedback
37 | 3.5 Monitoring and Control
38 | 3.5.1 Track customer satisfaction, retention, and service quality
39 | 3.5.2 Address operational inefficiencies and improve service offerings
40 | 3.5.3 Conduct weekly review meetings for performance evaluation
41 | 4.0 Project Closing Phase
42 | 4.1 Final Review and Closure
43 | 4.1.1 Document lessons learned, financial analysis, and customer insights
44 | 4.1.2 Prepare recommendations for future expansion and service enhancements